## Example Transition Plan
SA8000:2026 Transition Plan Template for Certification Bodies This example Transition Plan provides a clear structure for Certification Bodies (CABs) to manage their transition from SA8000:2014 to SA8000:2026 in line with SAI Notification 1 (May 12, 2025). It defines who does what, when, how, and the required evidence of completion. Any similar format is permitted if it contains the same information.
No. | Action / Activity | Responsibility (Who) | Timeframe (When) | Method / Process (How) | Evidence of Completion
1 | Conduct initial gap analysis between SA8000:2014 and SA8000:2026 | CAB SA8K Programme Manager, Certification Manager | By 31 Dec 2025 | Review all clauses, map against SAAS Procedure 200 v4.2, prepare gap report | Gap Analysis Report approved by CAB Management
2 | Prepare and submit CAB transition plan to SAAS | SA8K Programme Manager / Certification Manager | By 31 Dec 2025 | Use this transition plan template, confirm timelines and responsible persons | Email submission to SAAS with acknowledgment
3 | Revise all CAB system documents (procedures, forms, templates, contracts, policies) | Certification Manager / Process Owners | By 30 Jun 2026 | Update in document control system per ISO 17021-1 requirements | Revised document list and approval records
4 | Develop and deliver training for auditors, reviewers, and programme staff on SA8000:2026 | SA8K Programme Manager + CAB Training Coordinator | Jan–Jun 2026 | Accredited SAI training modules, in-house sessions, competency tests | Training attendance lists + competence records
5 | Update audit tools (Audit Plan, Report, NC Form, TR Checklist, Certificate template) | SA8K Programme Manager/ Lead Auditors | By 31 Mar 2026 | Revise and validate templates using pilot audits | Final approved templates under document control
6 | Update application forms and contracts to include SA8000:2026 references | Sales / Operations / Legal | By 31 Mar 2026 | Review terms and conditions for new certification scope | Signed contract samples showing new version
7 | Communicate transition timeline and requirements to existing clients | SA8K Programme Manager / Country Managers | By 1 Jun 2026 | Email and website notice referencing SAI Notification 1 | Client communication record + copy of email
8 | Update IT and database systems (e.g., Siebel, Salesforce, SharePoint) with new codes and revision dates | CAB Systems Administrator /SA8K Programme Manager | By 31 May 2026 | Modify fields for SA8000:2026 version tracking | Screenshot or log showing active revision code
9 | Conduct internal audit to verify implementation of new requirements | Internal Audit Team | By 30 Jun 2026 | Internal audit based on ISO 17021-1 + SAAS Procedure 200 checklist | Audit report + closure of NCs
10 | Begin auditing to SA8000:2026 once approved by SAAS | CAB Audit Teams | From 1 Jan 2026 (on approval) | Apply SA8000:2026 tools and revised procedures | First SA8000:2026 audit report and review record
11 | Ensure all new and recertification audits conducted to SA8000:2026 | Certification Decision Team / Schedulers | By 1 Jan 2027 | Verify audit plan and certificate versions before issue | Certification decision record showing new standard
12 | Complete transition of all existing clients to SA8000:2026 | Country Managers / Client Managers | By 31 Dec 2028 | Plan recertification audits to 2026 standard per client | List of clients transitioned and certificate numbers
13 | Withdraw remaining SA8000:2014 certificates | Certification Manager / SA8K Programme Manager | By 1 Jan 2029 | Verify database closure of old certificates | Withdrawal notice and public listing update